## Sheet1
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Days
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Project Initiation | Days
Gather group members | 1 | 1 | 1 | 1 | 100% | bar: Days 1
Select dataset | 2 | 1 | 2 | 2 | 100% | bar: Days 2
Setup GitHub repository | 2 | 1 | 2 | 1 | 100% | Days 24: Actual Duration; Days 27: (lining)
Preparatory Work | [5 empty] | Days 24: Plan Duratioon; Days 27: Any color
Understand dataset structure | 3 | 2 | 2 | 3 | 100% | Days 24: According to Plan; Days 27: lining + color
Identify analysis tasks | 4 | 1 | 4 | 2 | 100% | Days 25: Delay; Days 27: lining after color
Define additional analysis task | 5 | 1 | 5 | 1 | 100% | bar: Days 5
Discuss software design approach | 6 | 2 | 6 | 2 | 100% | bar: Days 6 to Days 7
Prepare Project Plan
Create Project Overview | 5 | 1 | 5 | 2 | 100% | bar: Days 5 to Days 6; Days 27
Develop Work-Breakdown Structure | 6 | 2 | 6 | 4 | 100% | bar: Days 6 to Days 8; Days 27
Define Activity Definitions and estimates | 7 | 1 | 7 | 3 | 100% | bar: Days 7 to Days 8; Days 27
Build Gantt chart | 7 | 2 | 7 | 4 | 100% | bar: Days 7 to Days 9
Prepare Software Design Document
Create System Vision Statement | 6 | 1 | 6 | 2 | 100% | bar: Days 6 to Days 7
Identify and list user requirements | 7 | 1 | 7 | 1 | 100% | bar: Days 7
Identify and list software requirements | 7 | 1 | 7 | 1 | 100% | bar: Days 7
Define use cases and personas | 7 | 2 | 7 | 3 | 100% | bar: Days 7 to Days 9
List system components and design | 8 | 3 | 8 | 4 | 100% | bar: Days 8 to Days 11
UI Wireframe Design
Design early user interface wireframe/mock-ups | 10 | 2 | 10 | 4 | 100% | bar: Days 10 to Days 13
Refine and finalize wireframe design | 12 | 1 | 13 | 2 | 100% | bar: Days 12 to Days 14
Software Implementation and Testing
Implement Data Analysis Program
Set up project structure and environment | 8 | 1 | 19 | 1 | 100% | bar: Days 8 to Days 16
Data Analysis and insights | 9 | 2 | 19 | 3 | 100% | bar: Days 9 to Days 17
Develop user interface components | 10 | 3 | 21 | 3 | 100% | bar: Days 10 to Days 20
Implement data analysis algorithms with UI | 11 | 4 | 22 | 4 | 100% | bar: Days 11 to Days 22
Integrate 5 types of insight tools | 13 | 2 | 24 | 2 | 100% | bar: Days 13 to Days 22
Data visualization | 15 | 1 | 26 | 1 | 100% | bar: Days 15 to Days 23
Perform Unit Testing
Create test cases for data loading | 9 | 1 | 9 | 1 | 100% | bar: Days 9 to Days 17
Execute unit tests for UI components | 10 | 2 | 10 | 2 | 100% | bar: Days 10 to Days 19
Test Data Visualization features | 11 | 2 | 12 | 2 | 100% | bar: Days 11 to Days 20
Conduct unit tests for analysis | 11 | 3 | 11 | 3 | 100% | bar: Days 11 to Days 21
verify UI and analysis integration | 13 | 2 | 13 | 2 | 100% | bar: Days 13 to Days 22
Perform unit testing and debugging | 12 | 4 | 12 | 5 | 100% | bar: Days 12 to Days 24
Software Testing Report
Compile test cases and outcomes | 14 | 3 | 21 | 3 | 100% | bar: Days 14 to Days 23
Include coverage and evaluation details | 16 | 1 | 23 | 1 | 100% | bar: Days 16 to Days 23
Document acceptance testing results | 16 | 2 | 23 | 2 | 100% | bar: Days 16 to Days 24
Explain implementation and testing process | 18 | 1 | 25 | 1 | 100% | bar: Days 18 to Days 25
Prepare a User Manual | 19 | 1 | 26 | 1 | 100% | bar: Days 19 to Days 26
Executive Summary
Summarize project objectives and outcomes | 13 | 7 | 13 | 12 | 100% | bar: Days 13 to Days 24
Highlight key achievements and results | 17 | 5 | 17 | 10 | 100% | bar: Days 17 to Days 26
Include main findings and recommendations | 20 | 3 | 20 | 8 | 100% | bar: Days 20 to Days 27
Edit and proofread summary | 23 | 1 | 23 | 2 | 100% | bar: Days 23; Days 28
Update and review everything
Review Project plan, testing and summary reports | 9 | 7 | 9 | 14 | 100% | bar: Days 9 to Days 26
Revise and edit content | 13 | 3 | 13 | 6 | 100% | bar: Days 13 to Days 26
Track actual completion times | 15 | 1 | 15 | 3 | 100% | bar: Days 15 to Days 26
Regularly update Gantt chart | 10 | 6 | 10 | 12 | 100% | bar: Days 10 to Days 27
Git log text document | 15 | 1 | 15 | 4 | 100% | bar: Days 15 to Days 27
Finalize all documentation | 15 | 1 | 15 | 3 | 100% | bar: Days 15 to Days 28
Final Review and submission
Revise and finalize everything | 15 | 2 | 16 | 3 | 100% | bar: Days 15 to Days 29
Submit all project deliverables | 16 | 1 | 17 | 2 | 100% | bar: Days 16 to Days 29