## Sheet1
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Days
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Project Initiation | Days
Gather group members | 1 | 1 | 1 | 1 | 100% | bar: Days 1
Select dataset | 2 | 2 | 2 | 2 | 100% | bar: Days 2
Setup GitHub repository | 2 |  |  |  | 100% | bar: Days 2
Preparatory Work
Understand dataset structure |  |  |  |  | 100% | bar: Days 3 to Days 4
Identify analysis tasks |  |  |  |  | 100% | bar: Days 4
Define additional analysis task |  |  |  |  | 100% | bar: Days 5
Discuss software design approach |  |  |  |  | 100% | bar: Days 6 to Days 7
Prepare Project Plan
Create Project Overview |  |  |  |  | 100% | bar: Days 5
Develop Work-Breakdown Structure |  |  |  |  | continued | bar: Days 6 to Days 7
Define Activity Definitions and estimates |  |  |  |  | continued | bar: Days 7
Build Gantt chart |  |  |  |  | continued | bar: Days 7 to Days 8
Prepare Software Design Document
Create System Vision Statement |  |  |  |  | 100% | bar: Days 6
Identify and list user requirements |  |  |  |  | 100% | bar: Days 7
Identify and list software requirements |  |  |  |  | 100% | bar: Days 7
Define use cases and personas |  |  |  |  | 100% | bar: Days 7 to Days 8
List system components and design |  |  |  |  | 100% | bar: Days 8 to Days 10
UI Wireframe Design
Design early user interface wireframe/mock-ups |  |  |  |  | 100% | bar: Days 10 to Days 11
Refine and finalize wireframe design |  |  |  |  | 100% | bar: Days 12
Software Implementation and Testing
Implement Data Analysis Program
Set up project structure and environment |  |  |  |  | 0% | bar: Days 8
Implement data loading and preprocessing |  |  |  |  | 0% | bar: Days 9 to Days 10
Develop user interface components |  |  |  |  | 0% | bar: Days 10 to Days 12
Implement analysis algorithms |  |  |  |  | 0% | bar: Days 11 to Days 14
Integrate UI and analysis components |  |  |  |  | 0% | bar: Days 13 to Days 14
Perform Unit Testing
Create test cases for data loading |  |  |  |  | 0% | bar: Days 9
Execute unit tests for UI components |  |  |  |  | 0% | bar: Days 10 to Days 11
Conduct unit tests for analysis |  |  |  |  | 0% | bar: Days 11 to Days 13
verify UI and analysis integration |  |  |  |  | 0% | bar: Days 13 to Days 14
Perform unit testing and debugging |  |  |  |  | 0% | bar: Days 12 to Days 15
Software Testing Report
Compile test cases and outcomes |  |  |  |  | 0% | bar: Days 14 to Days 16
Include coverage and evaluation details |  |  |  |  | 0% | bar: Days 16
Document acceptance testing results |  |  |  |  | 0% | bar: Days 16 to Days 17
Explain implementation and testing process |  |  |  |  | 0% | bar: Days 18
Executive Summary
Summarize project objectives and outcomes |  |  |  |  | 0% | bar: Days 13 to Days 19
Highlight key achievements and results |  |  |  |  | 0% | bar: Days 17 to Days 21
Include main findings and recommendations |  |  |  |  | 0% | bar: Days 20 to Days 22
Edit and proofread summary |  |  |  |  | 0% | bar: Days 23
Final Review and submission
Review Project plan, testing and summary reports |  |  |  |  | continued | bar: Days 24 to Days 25
Revise and edit content |  |  |  |  | continued | bar: Days 25 to Days 26
Track actual completion times |  |  |  |  | continued | bar: Days 24 to Days 26
Regularly update Gantt chart |  |  |  |  | continued | bar: Days 27
Git log text document |  |  |  |  | continued | bar: Days 27
Finalize all documentation |  |  |  |  | continued | bar: Days 24 to Days 28
Final Review and submission
Revise and finalize everything |  |  |  |  | 0% | bar: Days 28 to Days 29
Submit all project deliverables |  |  |  |  | 0% | bar: Days 29